## TEMPLATE
Award Management Deliverables Calendar
Description | The Award Management Deliverables Calendar (see Standard 10, key action 1 on compass.crs.org) is an "at-a-glance" tracking tool that summarizes information from the donor award. Use this calendar to capture project deliverables to the donor and other compliance requirements, such as technical and financial reports and updated project design/technical/MEAL documents (i.e., M&E Plan, table of contents, logframe, detailed implementation plan [DIP], workplan, etc.). The project manager (PM) manages this calendar and presents it at the Start-Up Workshop (see Standard 7, key action 2) so that all project team members are clear on project deliverables and timing. During DIP development, include the specific tasks and responsibilities associated with preparing the deliverables in this calendar in the initial DIP (and each subsequent DIP). The PM will continue to update and use this calendar to track key donor compliance obligations.
Instructions for Filling out the Calendar (Initial calendar prepared by Project Manager, or interim PM if there is a hiring delay) | 1. Adjust the template to reflect the implementation timeframe for the approved project. 2. Fill in the project name, donor name, and project start and end dates. 3. Review the sample deliverables in the template below (not an exhaustive list), modify as needed (e.g., add/modify the frequency for reports), add new items as required by the donor, and delete any items not applicable to the project; add/delete columns to match the project implementation timeframe. 4. Insert specific dates for hard deadlines in the appropriate cell under the corresponding project year and month (or quarter, for out-years). 5. Delete these instructions, save, and circulate the calendar to the project team. 6. Update the calendar whenever there are changes to deliverables (e.g., due to an award modification), and update each year with specific dates for that year.
Project Name: | [18 empty] | Project Start Date (month 1):
Donor Name: | [18 empty] | Project End Date:
Deliverable | Project Year 1 | [11 empty] | Project Year 2 |  |  |  | Project Year 3 |  |  |  | Project Year 4 |  |  |  | Project Year 5
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4+
Technical Reporting to Donor
(SPECIFY PERIOD) report submitted to donor
(SPECIFY PERIOD) reports from partners to CRS
Annual reports submitted to donor
Annual reports from partners to CRS
Final report submitted to donor
Final report from partners to CRS
Financial Reporting to Donor
(SPECIFY PERIOD) report submitted to donor
(SPECIFY PERIOD) reports from partners to CRS
Annual reports to donor
Annual reports from partners
Final report to donor
Final report from partners
MEAL Deliverables
MEAL Plan
Revised design documents (e.g., ToC, Logframe)
Indicator performance tracking table (IPTT) or equivalent
DIP
Baseline scope of work (SOW)
Baseline Evaluation Report
Midterm Review Report
Final Evaluation Report
Environmental Compliance
Initial Environment Examination
Environment Monitoring and Mitigation Plan
Call forwards
Closeout
Closeout Plan
Inventory Report

## EXAMPLE
Award Management Deliverables Calendar - EXAMPLE (see decription and instructions in TEMPLATE sheet)
Project Name: Food for Peace Best Project Ever | [18 empty] | Project Start Date (month 1): October 1, 2017
Donor Name: USAID/Office of Food for Peace | [18 empty] | Project End Date: September 30, 2022
Deliverable | Project Year 1 | [11 empty] | Project Year 2 |  |  |  | Project Year 3 |  |  |  | Project Year 4 |  |  |  | Project Year 5
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4+
Technical Reporting to Donor
Quarterly report submitted to donor | Project Year 1 4: 2016-01-30; Project Year 1 7: 2016-04-30; Project Year 1 10: 2016-07-30; Project Year 2 2: x; Project Year 2 3: x; Project Year 2 4: x; Project Year 3 2: x; Project Year 3 3: x; Project Year 3 4: x; Project Year 4 2: x; Project Year 4 3: x; Project Year 4 4: x; Project Year 5 2: x; Project Year 5 3: x
Quarterly reports from partners to CRS | Project Year 1 4: 2016-01-10; Project Year 1 7: 2016-04-10; Project Year 1 10: 2016-07-10; Project Year 2 2: x; Project Year 2 3: x; Project Year 2 4: x; Project Year 3 2: x; Project Year 3 3: x; Project Year 3 4: x; Project Year 4 2: x; Project Year 4 3: x; Project Year 4 4: x; Project Year 5 2: x; Project Year 5 3: x
Annual reports submitted to donor | Project Year 2 1: 2016-10-30; Project Year 3 1: x; Project Year 4 1: x; Project Year 5 1: x
Annual reports from partners to CRS | Project Year 2 1: 2016-10-10; Project Year 3 1: x; Project Year 4 1: x; Project Year 5 1: x
Final report submitted to donor | Project Year 5 4+: 2022-12-30
Final report from partners to CRS | Project Year 5 4+: 2022-12-10
Financial Reporting to Donor
Quarterly report submitted to donor | Project Year 1 4: 2016-01-30; Project Year 1 7: 2016-04-30; Project Year 1 10: 2016-07-30; Project Year 2 2: x; Project Year 2 3: x; Project Year 2 4: x; Project Year 3 2: x; Project Year 3 3: x; Project Year 3 4: x; Project Year 4 2: x; Project Year 4 3: x; Project Year 4 4: x; Project Year 5 2: x; Project Year 5 3: x
Quarterly reports from partners to CRS | Project Year 1 4: 2016-01-10; Project Year 1 7: 2016-04-10; Project Year 1 10: 2016-07-10; Project Year 2 2: x; Project Year 2 3: x; Project Year 2 4: x; Project Year 3 2: x; Project Year 3 3: x; Project Year 3 4: x; Project Year 4 2: x; Project Year 4 3: x; Project Year 4 4: x; Project Year 5 2: x; Project Year 5 3: x
Annual reports to Donor | Project Year 2 1: 2016-10-30; Project Year 3 1: x; Project Year 4 1: x; Project Year 5 1: x
Annual reports from partners | Project Year 2 1: 2016-10-10; Project Year 3 1: x; Project Year 4 1: x; Project Year 5 1: x
Final report to Donor | Project Year 5 4+: 2022-12-30
Final report from partners | Project Year 5 4+: 2022-12-10
MEAL Deliverables
MEAL Plan | Project Year 1 3: 2016-12-30
Revised design documents (e.g. ToC, Logframe) | Project Year 1 3: 2016-12-30
IPTT | Project Year 1 3: 2016-12-30
DIP | Project Year 1 3: 2016-12-30
Baseline SOW
Baseline Evaluation Report | Project Year 1 6: 2016-03-30
Midterm Review Report | Project Year 2 3: 2016-05-30
Final Evaluation Report | Project Year 5 4+: 2016-12-30
Environmental Compliance
Initial Environment Examination | Project Year 1 3: 2016-12-30
Environment Monitoring and Mitigation Plan | Project Year 1 6: 2016-03-30
Call forwards
Closeout
Closeout Plan | Project Year 5 4+: 2016-09-30
Inventory Report | Project Year 5 4+: 2016-12-30